## Sheet1
Task Name	Start Date	Duration	End Date

Research PET Scanners	31/05/18	25	24/06/18
Research Alternative Solutions	11/06/18	14	24/06/18
Research Kinect Camera	11/06/18	14	24/06/18
Research Point Cloud Library	11/06/18	14	24/06/18
Write initial report	31/05/18	26	25/06/18
Edit initial Report	11/06/18	15	25/06/18
Port STIR framework to Windows	11/06/18	14	24/06/18
Read data from the Kinect	11/06/18	7	17/06/18
Create stand-alone console application to interface with Kinect	25/06/18	7	01/07/18
Add ability to save point cloud from Kinect to file or data type	25/06/18	7	01/07/18
Add ability to output multiple point clouds per execution	25/06/18	7	01/07/18
Add ability to timestamp output	25/06/18	7	01/07/18
Add ability to clean point clouds	02/07/18	14	15/07/18
Add ability to register between point clouds	02/07/18	21	22/07/18
Add ability to extract vector field or translation from registered point clouds	09/07/18	21	29/07/18
Add ability to remove extraneous data from point cloud	16/07/18	14	29/07/18
Add ability to synchronise timestamp on point cloud to output from scanner	13/08/18	14	26/08/18
Add ability to translate camera space to scanner space	13/08/18	14	26/08/18
Add ability to apply output from application to output from scanner	20/08/18	21	09/09/18
Write final report	30/07/18	54	21/09/18
Edit final report	27/08/18	26	21/09/18
Port application to Windows	03/09/18	13	15/09/18
Add application to the Windows version of STIR as library	03/09/18	13	15/09/18