## Sheet1
Task Name | Start Date | Duration | End Date
Research PET Scanners | 2018-05-31 | 25 | 2018-06-24
Research Alternative Solutions | 2018-06-11 | 14 | 2018-06-24
Research Kinect Camera | 2018-06-11 | 14 | 2018-06-24
Research Point Cloud Library | 2018-06-11 | 14 | 2018-06-24
Write initial report | 2018-05-31 | 26 | 2018-06-25
Edit initial Report | 2018-06-11 | 15 | 2018-06-25
Port STIR framework to Windows | 2018-06-11 | 14 | 2018-06-24
Read data from the Kinect | 2018-06-11 | 7 | 2018-06-17
Create stand-alone console application to interface with Kinect | 2018-06-25 | 7 | 2018-07-01
Add ability to save point cloud from Kinect to file or data type | 2018-06-25 | 7 | 2018-07-01
Add ability to output multiple point clouds per execution | 2018-06-25 | 7 | 2018-07-01
Add ability to timestamp output | 2018-06-25 | 7 | 2018-07-01
Add ability to clean point clouds | 2018-07-02 | 14 | 2018-07-15
Add ability to register between point clouds | 2018-07-02 | 21 | 2018-07-22
Add ability to extract vector field or translation from registered point clouds | 2018-07-09 | 21 | 2018-07-29
Add ability to remove extraneous data from point cloud | 2018-07-16 | 14 | 2018-07-29
Add ability to synchronise timestamp on point cloud to output from scanner | 2018-08-13 | 14 | 2018-08-26
Add ability to translate camera space to scanner space | 2018-08-13 | 14 | 2018-08-26
Add ability to apply output from application to output from scanner | 2018-08-20 | 21 | 2018-09-09
Write final report | 2018-07-30 | 54 | 2018-09-21
Edit final report | 2018-08-27 | 26 | 2018-09-21
Port application to Windows | 2018-09-03 | 13 | 2018-09-15
Add application to the Windows version of STIR as library | 2018-09-03 | 13 | 2018-09-15