## Sheet1
Task Name	Start Date	Duration	End Date

Research PET Scanners	31/05/18	29	28/06/18
Research Alternative Solutions	07/06/18	22	28/06/18
Research Kinect Camera	07/06/18	22	28/06/18
Research Point Cloud Library	07/06/18	22	28/06/18
Write initial report	31/05/18	26	25/06/18
Edit initial Report	14/06/18	12	25/06/18
Read data from the Kinect	28/06/18	8	05/07/18
Create stand-alone application to interface with Kinect	28/06/18	15	12/07/18
Add ability to control the tilt motor of the Kinect	05/07/18	15	19/07/18
Add ability to extract depth and/or RGB images from kinect	12/07/18	15	26/07/18
Add ability to save depth and/or RGB images from Kinect to text or binary file	12/07/18	15	26/07/18
Add ability to output multiple depth and/or RGB images per execution	19/07/18	8	26/07/18
Add ability to timestamp output with timestamp relative to Kinect	19/07/18	8	26/07/18
Add ability to change output settings for the depth and/or RGB images	19/07/18	8	26/07/18
Add ability to output header files for the depth and/or RGB images	26/07/18	15	09/08/18
Create stand-alone application to load the header output from the Kinect application	26/07/18	15	09/08/18
Add ability to load data from header file	26/07/18	15	09/08/18
Research calculating point clouds from the loaded data	05/07/18	22	26/07/18
Add ability to calculate point clouds from the loaded data	05/07/18	22	26/07/18
Add ability to calculate centre of gravity for the point clouds	02/08/18	8	09/08/18
Add ability to visualise the point clouds and centres of gravity	02/08/18	15	16/08/18
Research point cloud processing	02/08/18	8	09/08/18
Add ability to globally threshold point clouds	02/08/18	8	09/08/18
Add ability to de-noise point clouds	02/08/18	8	09/08/18
Add ability to downsample point clouds	02/08/18	8	09/08/18
Research point cloud registration	02/08/18	43	13/09/18
Add ability to register between point clouds	02/08/18	15	16/08/18
Add ability to use output of previous registration as input to next registration	09/08/18	8	16/08/18
Add ability to extract motion signal from registration output	09/08/18	8	16/08/18
Add ability to asses amount of movement between point clouds	09/08/18	8	16/08/18
Add ability to skip processing based on amount of movement between point clouds	09/08/18	15	23/08/18
Add ability to extract motion signal from movement between point clouds	09/08/18	15	23/08/18
Research point cloud tracking	02/08/18	43	13/09/18
Add ability to track a region of the point clouds	16/08/18	29	13/09/18
Add ability to extract motion signal from the tracked region of the point clouds	16/08/18	8	23/08/18
Add ability to change output settings and values for registration and motion signal extraction	16/08/18	8	23/08/18
Add ability to save values and output of registration and motion signal extraction to a text or binary file	02/08/18	22	23/08/18
Write final report	13/08/18	32	13/09/18
Edit final report	06/09/18	8	13/09/18